## Product Backlogs
ID | Backlog Items | Description | Sprint
1 | User Management | Includes login, user registration, profile, and password management features. Covers backend, frontend, database integration, and testing. | 2
2 | Building & Checklist Management | Manage campus buildings and configure inspection checklists. Covers backend, frontend, database integration, and testing. | 2
3 | Checklist Form Submission | Allow the technicians/Admin to Select the building and submit the checklist for a particular date | 2
4 | History Management | View and edit submission history for technicians and admins; includes frontend, backend, and testing. | 3
5 | Reporting and Analytics | Generate reports with filtering options (building, technician, date range), CSV export, and UI support. | 3
6 | Raise Issue / Report an Issue | Enable technicians to report building-related issues and allow admins to manage responses, with status tracking and UI support. | 3

## Sprint 2 Backlogs
Item ID | Product Backlog Item | Task | Sub Task | Task Description | Task to be done by | Status
1 | User Management | Login | Backend development | Implement secure login API with password hashing and session management | Adarsh, Jeevitha | To Do
|  |  | Frontend development | Create login form UI with validation for required fields. | Hitesh, Filipe | To Do
|  |  | Testing the functionality | Verify successful/failed logins, error handling, and session timeout. | Keerthi | To Do
|  | User registration | Backend development | Build registration API to store technician details securely and assign roles. | Adarsh, Filipe | To Do
|  |  | Frontend development | Design registration form with field validations (email, password strength, required fields). | Filipe, Jeevitha | To Do
|  |  | Database Integration | Store user details securely. | Hitesh | To Do
|  |  | Testing the functionality | Ensure new users are saved correctly, duplicates prevented, and role assigned | Keerthi | To Do
|  | User profile management | Backend development | Implement APIs to view/update profile details (contact info, password, etc.). | Adarsh, Keerthi | To Do
|  |  | Frontend development | Build profile page UI for editing/updating information. | Filipe, Jeevitha | To Do
|  |  | Testing the functionality | Verify updates are saved correctly and only accessible by the logged-in user. | Hitesh | To Do
|  | Password Management/Reset | Backend development | Implement password reset/change logic with hashing and validation. | Adarsh, Hitesh | To Do
|  |  | Frontend development | Create UI for reset/change password with form validation. | Filipe, Keerthi | To Do
|  |  | Testing the functionality | Confirm password updates work and enforce strong password rules. | Jeevitha | To Do
2 | Building & Checklist Management | Building Management | Backend development | Create APIs to add, update, delete, and list campus buildings. | Adarsh, Hitesh | To Do
|  |  | Frontend development | Develop UI to allow Admins to manage campus buildings. | Filipe, Jeevitha | To Do
|  |  | Database Integration | Store building details in the database securely. | Hitesh | To Do
|  |  | Testing the functionality | Verify building CRUD operations and role restrictions. | Keerthi | To Do
|  | Checklist Configuration | Backend development | Implement APIs to create and configure inspection checklists with different data types. | Adarsh, Keerthi | To Do
|  |  | Frontend development | Develop UI for Admins to configure and view building-specific checklists. | Filipe, Jeevitha | To Do
|  |  | Database Integration | Store checklist items with data type and validation rules. | Hitesh | To Do
|  |  | Testing the functionality | Verify correct checklist creation, validation, and association with buildings. | Keerthi | To Do
3 | Checklist Form Submission | Backend | Api Endpoint | Create Api to submit the building data/checklist form for a particular date | Adarsh | To Do
|  | Frontend | Date and Building filter | Create the dropdown for building selection and a select data element | Jeevitha | To Do
|  |  | checklist form page | Create frontend component for building checklist/data submission | Feilipe | To Do

## Sprint 3 Backlogs
Item ID | Product Backlog Item | Task | Sub Task | Task Description | Task to be done by | Status
4 | History Management | Submission History | Backend development | Implement APIs to view/edit submission history for technicians and admins. | Adarsh, Hitesh | To Do
|  |  | Frontend development | Develop UI to allow users to view/edit past submissions based on Roles. | Filipe, Jeevitha | To Do
|  |  | Testing the functionality | Verify access controls for viewing/editing history. | Keerthi | To Do
5 | Reporting and Analytics | Report generation | Backend development | Build API to filter inspection data by building, technician, or date range. | Adarsh, Hitesh | To Do
|  |  | Frontend development | Create UI to generate and download reports (CSV). | Filipe, Keerthi | To Do
|  |  | Testing the functionality | Validate report accuracy, filtering, and CSV export. | Jeevitha | To Do
6 | Raise Issue/Report an Issue | Issue Reporting | Backend development | Build API for technicians to raise building-related issues with status tracking. | Adarsh, Hitesh | To Do
|  |  | Frontend development | Create UI for technicians to raise issues and admins to manage responses. | Filipe, Jeevitha | To Do
|  |  | Testing the functionality | Ensure issues are logged correctly, linked to buildings, and status updates work. | Keerthi | To Do